## 1
DEFECT_ID | DEFECT_001
MODULE | LOGIN
SUMMARY | USER IS UNABLE TO LOGIN USING MOBILE NUMBER
DESCRIPTION | USER IS ABLE TO LOGIN WITH OTHER POSSIBLE WAYS EXCEPT USING MOBILE NUMBER
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: REGISTER WITH VALID DETAILS STEP 3: CLICK ON LOGIN LINK STEP 4:ENTER MOBILE NUMBER AND CLICK ON SUBMIT
EXPECTED RESULT | SYSTEM SHOULD VALIDATES AND USER SHOULD BE ABLE TO NAVIAGTE TO HOME PAGE IF THE MOBILE NUMBER IS VALID
ACTUAL RESULT | SYSTEM IS NOT RESPONDING
SEVERITY | CRITICAL
PRIORITY | MAJOR
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1dg2xzHfFqkCGSNrAQE6BBFzdlYG4gJow/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 10
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 2
DEFECT_ID | DEFECT_002
MODULE | MY ACCOUNT / ADDRESS DETAILS
SUMMARY | MULTIPLE FIELDS IN MY ACCOUNT ACCEPT INVALID INPUT WITHOUT ANY VALIDATION OR LENGTH RESTRICTIONS
DESCRIPTION | IN THE MY ACCOUNT → ADDRESS SECTION, INPUT FIELDS SUCH AS FIRST NAME, LAST NAME, COMPANY, CITY, ADDRESS 1, ADDRESS 2, ZIP CODE, AND PHONE NUMBER ACCEPT RANDOM VALUES INCLUDING NUMBERS, SPECIAL CHARACTERS, AND IRRELEVANT TEXT. THERE IS NO VALIDATION FOR INPUT TYPE, AND NO MINIMUM OR MAXIMUM LENGTH RESTRICTIONS ARE ENFORCED, ALLOWING USERS TO ENTER INVALID DATA.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: LOGIN WITH VALID USER CREDENTIALS STEP 3: NAVIGATE TO MY ACCOUNT STEP 4: CLICK ON ADDRESSES / EDIT ADDRESS STEP 5: ENTER RANDOM VALUES (E.G. @@@123, ###, ABC123!!) IN ALL FIELDS STEP 6: CLICK SAVE / UPDATE STEP 7: OBSERVE THAT INVALID DATA IS ACCEPTED WITHOUT ANY ERROR
EXPECTED RESULT | SYSTEM SHOULD VALIDATE EACH FIELD BASED ON ITS TYPE (E.G., NAME FIELDS SHOULD ACCEPT ONLY ALPHABETS, PHONE NUMBER SHOULD ACCEPT ONLY NUMBERS). ALSO, PROPER MINIMUM AND MAXIMUM LENGTH VALIDATIONS SHOULD BE APPLIED AND ERROR MESSAGES SHOULD BE DISPLAYED FOR INVALID INPUT.
ACTUAL RESULT | ALL FIELDS ACCEPT RANDOM INPUT INCLUDING SPECIAL CHARACTERS AND NUMBERS WITHOUT ANY VALIDATION OR ERROR MESSAGE
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/12h3KfWpqs9Tr2q5RcsdcauAwxcoaGW-a/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION | LATEST
BUILD VERSION | NA
#NAME?

## 3
DEFECT_ID | DEFECT_003
MODULE | COMPARE PRODUCTS
SUMMARY | COMPARE PRODUCTS FEATURE DOES NOT PROVIDE PROPER COMPARISON AND LACKS DIRECT ACCESS OPTION
DESCRIPTION | THE COMPARE PRODUCTS PAGE DOES NOT DISPLAY DETAILED COMPARISON BETWEEN PRODUCTS. ONLY PRICE INFORMATION IS SHOWN, WHILE OTHER IMPORTANT ATTRIBUTES ARE MISSING. ADDITIONALLY, THERE IS NO DIRECT BUTTON OR OPTION AVAILABLE ON PRODUCT PAGES TO VIEW COMPARED PRODUCTS. THE ONLY ACCESS TO THIS FEATURE IS THROUGH THE FOOTER UNDER CUSTOMER SERVICE, WHICH AFFECTS USABILITY.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: NAVIGATE TO ANY PRODUCT CATEGORY STEP 3: ADD MULTIPLE PRODUCTS TO COMPARE LIST (IF OPTION AVAILABLE) STEP 4: SCROLL DOWN TO FOOTER SECTION STEP 5: CLICK ON "COMPARE PRODUCTS LIST" UNDER CUSTOMER SERVICE STEP 6: OBSERVE THE COMPARISON PAGE
EXPECTED RESULT | SYSTEM SHOULD DISPLAY COMPLETE PRODUCT COMPARISON INCLUDING FEATURES, SPECIFICATIONS, AND ATTRIBUTES. ALSO, A CLEAR AND VISIBLE "COMPARE PRODUCTS" BUTTON SHOULD BE AVAILABLE FOR EASY ACCESS.
ACTUAL RESULT | ONLY PRICE IS DISPLAYED FOR COMPARISON AND THERE IS NO DIRECT OPTION OR BUTTON TO ACCESS COMPARE PRODUCTS EXCEPT THROUGH THE FOOTER LINK
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1LMaJOab-yIO-oI197EuPpjIPgi3-Qg56/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION | LATEST
BUILD VERSION | NA
#NAME?

## 4
DEFECT_ID | DEFECT_004
MODULE | LOGIN / PASSWORD RECOVERY
SUMMARY | FORGOT PASSWORD FUNCTIONALITY DOES NOT SEND RESET EMAIL TO USER
DESCRIPTION | WHEN THE USER ENTERS A VALID REGISTERED EMAIL ADDRESS IN THE PASSWORD RECOVERY PAGE AND CLICKS ON THE RECOVER BUTTON, THE SYSTEM DOES NOT SEND ANY PASSWORD RESET EMAIL. AS A RESULT, THE USER IS UNABLE TO RESET THE PASSWORD, MAKING THE FORGOT PASSWORD FEATURE NON-FUNCTIONAL.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: CLICK ON LOGIN BUTTON STEP 3: CLICK ON FORGOT PASSWORD LINK STEP 4: ENTER REGISTERED EMAIL ADDRESS IN EMAIL FIELD STEP 5: CLICK ON RECOVER BUTTON STEP 6: CHECK THE REGISTERED EMAIL INBOX STEP 7: OBSERVE THAT NO PASSWORD RESET EMAIL IS RECEIVED
EXPECTED RESULT | SYSTEM SHOULD SEND A PASSWORD RESET LINK TO THE REGISTERED EMAIL ADDRESS AND ALLOW THE USER TO RESET THE PASSWORD SUCCESSFULLY
ACTUAL RESULT | NO EMAIL IS RECEIVED AFTER CLICKING ON RECOVER, AND PASSWORD RESET PROCESS DOES NOT INITIATE
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/145xpeIl3U3ozMzvL8LHXnmuvu1DbSC0V/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 5
DEFECT_ID | DEFECT_005
MODULE | USER REGISTRATION
SUMMARY | FIRST NAME AND LAST NAME FIELD ALLOWS NUMERIC AND SPECIAL CHARACTERS DURING USER REGISTRATION
DESCRIPTION | WHEN A USER ATTEMPTS TO CREATE A NEW ACCOUNT, THE FIRST NAME AND LAST NAME FIELD ACCEPTS INVALID INPUT SUCH AS NUMBERS AND SPECIAL CHARACTERS AND STILL COMPLETES THE REGISTRATION PROCESS WITHOUT SHOWING ANY VALIDATION MESSAGE. HOWEVER, THE LAST NAME FIELD IS EXPECTED TO ACCEPT ONLY ALPHABETIC CHARACTERS.AND THERE IS NO SPECIFIC LENGTH IT EVEN ACCEPTS ONE CHARACTER AS LAST NAME AND FIRST NAME
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: CLICK ON THE "REGISTER" OPTION FROM THE TOP MENU STEP 3: GO TO THE REGISTRATION PAGE STEP 4: ENTER A VALID FIRST NAME STEP 5: PROVIDE INVALID INPUT (NUMBERS OR SPECIAL CHARACTERS) IN THE LAST NAME FIELD STEP 6: FILL ALL OTHER REQUIRED FIELDS WITH VALID INFORMATION STEP 7: CLICK ON THE "REGISTER" BUTTON STEP 8: VERIFY THE SYSTEM RESPONSE
EXPECTED RESULT | THE SYSTEM SHOULD DISPLAY AN ERROR MESSAGE LIKE "LAST NAME SHOULD CONTAIN ONLY ALPHABETS" AND SHOULD PREVENT THE USER FROM REGISTERING WITH INVALID INPUT IN THE LAST NAME FIELD
ACTUAL RESULT | THE SYSTEM ACCEPTS INVALID CHARACTERS IN THE LAST NAME FIELD AND SUCCESSFULLY COMPLETES THE REGISTRATION WITHOUT ANY ERROR MESSAGE
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/12h3KfWpqs9Tr2q5RcsdcauAwxcoaGW-a/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 6
DEFECT_ID | DEFECT_006
MODULE | LOGIN / AUTHENTICATION
SUMMARY | USER UNABLE TO LOGIN WITH SAME CREDENTIALS AFTER LOGOUT OR AFTER SOME TIME
DESCRIPTION | AFTER SUCCESSFUL REGISTRATION AND LOGIN, WHEN THE USER LOGS OUT AND ATTEMPTS TO LOGIN AGAIN AFTER SOME TIME (E.G., 30 MINUTES), THE SYSTEM DISPLAYS AN "INVALID EMAIL OR PASSWORD" ERROR EVEN THOUGH THE ENTERED CREDENTIALS ARE CORRECT. THIS INDICATES A SESSION OR DATA VALIDATION ISSUE.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: REGISTER A NEW USER WITH VALID EMAIL AND PASSWORD STEP 3: LOGIN USING THE REGISTERED CREDENTIALS STEP 4: LOGOUT FROM THE APPLICATION STEP 5: WAIT FOR SOME TIME (E.G., 30 MINUTES) STEP 6: TRY TO LOGIN AGAIN USING THE SAME EMAIL AND PASSWORD
EXPECTED RESULT | USER SHOULD BE ABLE TO LOGIN SUCCESSFULLY USING THE SAME VALID CREDENTIALS EVEN AFTER LOGOUT OR TIME DELAY
ACTUAL RESULT | SYSTEM SHOWS "INVALID EMAIL OR PASSWORD" ERROR EVEN WHEN CORRECT CREDENTIALS ARE ENTERED
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/10L2C6aI-KXbE9kdMCG4cDrULzcnRQyLw/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 7
DEFECT_ID | DEFECT_007
MODULE | CART / SHIPPING ESTIMATION
SUMMARY | POSTAL CODE FIELD IN ESTIMATE SHIPPING ACCEPTS INVALID CHARACTERS AFTER ADDING PRODUCT TO CART
DESCRIPTION | WHEN A USER ADDS A PRODUCT TO THE CART FROM CATEGORIES AND PROCEEDS TO THE "ESTIMATE SHIPPING" OPTION, THE POSTAL CODE FIELD ACCEPTS RANDOM INPUT SUCH AS SPECIAL CHARACTERS AND ALPHANUMERIC VALUES WITHOUT ANY VALIDATION. THE SYSTEM DOES NOT RESTRICT INVALID FORMATS, WHICH MAY LEAD TO INCORRECT SHIPPING CALCULATIONS.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: NAVIGATE TO ANY PRODUCT CATEGORY STEP 3: ADD A PRODUCT TO THE CART STEP 4: GO TO SHOPPING CART PAGE STEP 5: CLICK ON "ESTIMATE SHIPPING" STEP 6: ENTER INVALID POSTAL CODE (E.G. "@@123ABC!!") STEP 7: CLICK ON APPLY BUTTON
EXPECTED RESULT | SYSTEM SHOULD VALIDATE THE POSTAL CODE FIELD AND ALLOW ONLY VALID FORMAT (NUMERIC OR STANDARD FORMAT BASED ON REGION) AND DISPLAY ERROR MESSAGE FOR INVALID INPUT
ACTUAL RESULT | POSTAL CODE FIELD ACCEPTS SPECIAL CHARACTERS AND RANDOM VALUES WITHOUT SHOWING ANY VALIDATION ERROR
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/1hboEQdimjgXSVoimNLK5C_uNblLfoc9h/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 8
DEFECT_ID | DEFECT_008
MODULE | CHECKOUT
SUMMARY | PHONE NUMBER FIELD ALLOWS ALPHABETS AND SPECIAL CHARACTERS DURING CHECKOUT
DESCRIPTION | DURING THE CHECKOUT PROCESS, THE PHONE NUMBER FIELD DOES NOT VALIDATE USER INPUT PROPERLY. IT ACCEPTS LETTERS AND SPECIAL CHARACTERS, ALLOWING USERS TO PROCEED WITH INVALID PHONE NUMBER DATA WITHOUT ANY ERROR MESSAGE.
STEPS TO REPRODUCE | STEP 1:OPEN THE APPLICATION STEP 2:ADD ANY PRODUCT TO THE SHOPPING CART STEP 3:PROCEED TO CHECKOUT STEP 4:ENTER BILLING DETAILS AND PROVIDE INVALID INPUT (LETTERS/SPECIAL CHARACTERS) IN PHONE NUMBER FIELD STEP 5:CLICK CONTINUE / SUBMIT
EXPECTED RESULT | PHONE NUMBER FIELD SHOULD ACCEPT ONLY NUMERIC VALUES AND DISPLAY A VALIDATION ERROR MESSAGE WHEN INVALID INPUT IS ENTERED
ACTUAL RESULT | SYSTEM ACCEPTS ALPHABETS AND SPECIAL CHARACTERS IN THE PHONE NUMBER FIELD AND ALLOWS CHECKOUT WITHOUT SHOWING ANY VALIDATION ERROR
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL DEFECT
ATTACHMENTS | https://drive.google.com/file/d/12h3KfWpqs9Tr2q5RcsdcauAwxcoaGW-a/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 9
DEFECT_ID | DEFECT_009
MODULE | FOOTER / NEWSFEED NAVIGATION
SUMMARY | CLICKING ON NEWSFEED LINK IN FOOTER REDIRECTS TO PAGE DISPLAYING EMBEDDED CONTENT INSTEAD OF EXPECTED INFORMATION PAGE
DESCRIPTION | WHILE ATTEMPTING TO ADD PRODUCTS TO THE WISHLIST, THE APPLICATION SHOWHEN USER CLICKS ON THE NEWSFEED OPTION AVAILABLE IN THE BOTTOM NAVIGATION PANEL, THE SYSTEM NAVIGATES TO A PAGE THAT SHOWS EMBEDDED OR IRRELEVANT CONTENT LINKS. THE DISPLAYED PAGE DOES NOT MATCH THE EXPECTED NEWS OR CONTENT VIEW.WS UNEXPECTED BEHAVIOR. INSTEAD OF ADDING THE ITEM, IT REDIRECTS THE USER TO ANOTHER PAGE. IN SOME CASES, THE PRODUCT IS NOT ADDED TO THE WISHLIST.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: SCROLL DOWN TO THE FOOTER SECTION STEP 3: CLICK ON NEWSFEED / NEWS LINK STEP 4: OBSERVE THE LOADED PAGE CONTENT
EXPECTED RESULT | SYSTEM SHOULD DISPLAY PROPER NEWS OR INFORMATION CONTENT PAGE WITHOUT EMBEDDED OR UNRELATED LINKS
ACTUAL RESULT | PAGE DISPLAYS EMBEDDED LINKS OR IRRELEVANT CONTENT INSTEAD OF EXPECTED NEWS INFORMATION
SEVERITY | MINOR
PRIORITY | MEDIUM
DEFECT TYPE | UI / FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/1hJTfjM6ZKOZGyY3oHh_vOZHvchrIHJTQ/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 10
DEFECT_ID | DEFECT_010
MODULE | WISHLIST
SUMMARY | CLICKING ON WISHLIST ICON NAVIGATES TO DIFFERENT PAGE AND PRODUCT IS NOT CONSISTENTLY ADDED
DESCRIPTION | WHILE ATTEMPTING TO ADD PRODUCTS TO THE WISHLIST, THE APPLICATION SHOWS UNEXPECTED BEHAVIOR. INSTEAD OF ADDING THE ITEM, IT REDIRECTS THE USER TO ANOTHER PAGE. IN SOME CASES, THE PRODUCT IS NOT ADDED TO THE WISHLIST.
STEPS TO REPRODUCE | STEPS TO REPRODUCE STEP 1: LAUNCH THE APPLICATION STEP 2: LOGIN USING VALID CREDENTIALS STEP 3: NAVIGATE TO PRODUCT LIST PAGE STEP 4: CLICK ON WISHLIST (HEART) ICON STEP 5: VERIFY WHETHER PRODUCT IS ADDED
EXPECTED RESULT | PRODUCT SHOULD BE ADDED TO WISHLIST SUCCESSFULLY WITHOUT REDIRECTION AND A CONFIRMATION MESSAGE SHOULD BE DISPLAYED
ACTUAL RESULT | SYSTEM REDIRECTS TO ANOTHER PAGE AND PRODUCT IS NOT ADDED IN SOME SCENARIOS
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/1r2b8pZT2QLSeXPiIdavUUEMfXXg12jk8/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 11
DEFECT_ID | DEFECT_011
MODULE | PRODUCT DETAILS / EMAIL A FRIEND
SUMMARY | “EMAIL A FRIEND” FEATURE IS NOT WORKING ON PRODUCT PAGE
DESCRIPTION | WHEN THE USER CLICKS ON THE “EMAIL A FRIEND” OPTION FROM THE PRODUCT DETAILS PAGE, THE FUNCTIONALITY DOES NOT WORK AS EXPECTED. EITHER THE PAGE DOES NOT LOAD PROPERLY OR THE EMAIL IS NOT SENT AFTER PROVIDING REQUIRED DETAILS, MAKING THE FEATURE NON-FUNCTIONAL.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: NAVIGATE TO ANY PRODUCT PAGE STEP 3: CLICK ON “EMAIL A FRIEND” OPTION STEP 4: ENTER REQUIRED EMAIL DETAILS (SENDER & RECEIVER EMAIL) STEP 5: CLICK SEND BUTTON STEP 6: CHECK WHETHER EMAIL IS RECEIVED
EXPECTED RESULT | SYSTEM SHOULD OPEN EMAIL FORM AND SUCCESSFULLY SEND PRODUCT DETAILS TO THE SPECIFIED EMAIL ADDRESS AFTER SUBMISSION
ACTUAL RESULT | EMAIL IS NOT SENT OR FUNCTION DOES NOT RESPOND PROPERLY AFTER CLICKING “EMAIL A FRIEND”
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/1D1180vwdsPQZoSQTXSstn8I6X0foZEq5/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 12
DEFECT_ID | DEFECT_012
MODULE | MY ACCOUNT / ADDRESS FORM
SUMMARY | CITY DOES NOT UPDATE BASED ON SELECTED COUNTRY
DESCRIPTION | WHEN THE USER SELECTS A SPECIFIC COUNTRY IN THE ADDRESS FORM, THE CITY DOES NOT DISPLAY THE CORRESPONDING CITY FOR THAT COUNTRY. INSTEAD, IT EITHER SHOWS INCORRECT VALUES OR DOES NOT UPDATE DYNAMICALLY, LEADING TO INVALID LOCATION SELECTION.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: LOGIN WITH VALID USER CREDENTIALS STEP 3: NAVIGATE TO MY ACCOUNT → ADDRESSES STEP 4: CLICK ON ADD NEW / EDIT ADDRESS STEP 5: SELECT ANY COUNTRY FROM COUNTRY DROPDOWN STEP 6: CHECK STATE/PROVINCE DROPDOWN OPTIONS STEP 7: OBSERVE THAT STATES ARE NOT UPDATED BASED ON SELECTED COUNTRY
EXPECTED RESULT | CITYLIST SHOULD DYNAMICALLY UPDATE BASED ON THE SELECTED COUNTRY AND DISPLAY ONLY RELEVANT STATES
ACTUAL RESULT | CITY DROPDOWN DOES NOT CHANGE OR SHOWS INCORRECT/UNRELATED OPTIONS AFTER SELECTING A COUNTRY
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/12h3KfWpqs9Tr2q5RcsdcauAwxcoaGW-a/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 13
DEFECT_ID | DEFECT_013
MODULE | MY ACCOUNT / CHANGE PASSWORD
SUMMARY | SYSTEM ACCEPTS WEAK PASSWORDS WITHOUT ENFORCING PASSWORD COMPLEXITY RULES
DESCRIPTION | IN THE CHANGE PASSWORD FUNCTIONALITY, THE SYSTEM ALLOWS USERS TO SET VERY WEAK PASSWORDS SUCH AS "123456" WITHOUT ANY VALIDATION. THERE ARE NO ENFORCEMENT RULES LIKE MINIMUM LENGTH, UPPERCASE, LOWERCASE, NUMBERS, OR SPECIAL CHARACTERS, WHICH COMPROMISES ACCOUNT SECURITY.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: LOGIN WITH VALID USER CREDENTIALS STEP 3: NAVIGATE TO MY ACCOUNT → CHANGE PASSWORD STEP 4: ENTER CURRENT PASSWORD STEP 5: ENTER WEAK PASSWORD (E.G. 123456) IN NEW PASSWORD FIELD STEP 6: CONFIRM THE SAME PASSWORD STEP 7: CLICK ON CHANGE PASSWORD BUTTON STEP 8: OBSERVE THAT PASSWORD IS ACCEPTED WITHOUT VALIDATION
EXPECTED RESULT | SYSTEM SHOULD ENFORCE STRONG PASSWORD POLICIES SUCH AS MINIMUM LENGTH AND REQUIREMENT OF ALPHANUMERIC CHARACTERS WITH AT LEAST ONE SPECIAL CHARACTER, AND DISPLAY ERROR MESSAGE FOR WEAK PASSWORDS
ACTUAL RESULT | SYSTEM ACCEPTS SIMPLE AND WEAK PASSWORDS (E.G., "123456") WITHOUT ANY VALIDATION OR ERROR MESSAGE
SEVERITY | CRITICAL
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/16pbDZVrAcnSJwfy8keLqRGSM6GvG-car/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 14
DEFECT_ID | DEFECT_014
MODULE | PRODUCT DETAILS / REVIEW SECTION
SUMMARY | REVIEW TEXT FIELD DOES NOT ENFORCE MINIMUM OR MAXIMUM CHARACTER LIMIT
DESCRIPTION | IN THE PRODUCT REVIEW SECTION, THE REVIEW TEXT FIELD ACCEPTS INPUT OF ANY LENGTH WITHOUT APPLYING ANY MINIMUM OR MAXIMUM CHARACTER RESTRICTION. USERS CAN SUBMIT VERY SHORT OR EXTREMELY LONG REVIEWS, WHICH MAY AFFECT DATA QUALITY AND USER EXPERIENCE.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: NAVIGATE TO ANY PRODUCT PAGE STEP 3: SCROLL DOWN TO REVIEW SECTION STEP 4: ENTER VERY LONG OR VERY SHORT TEXT IN REVIEW FIELD STEP 5: SELECT RATING STEP 6: CLICK ON SUBMIT REVIEW STEP 7: OBSERVE THAT REVIEW IS ACCEPTED WITHOUT LENGTH VALIDATION
EXPECTED RESULT | SYSTEM SHOULD ENFORCE CHARACTER LIMITS FOR REVIEW TEXT (E.G., MINIMUM AND MAXIMUM LENGTH) AND DISPLAY VALIDATION MESSAGE WHEN LIMIT IS NOT MET
ACTUAL RESULT | REVIEW FIELD ACCEPTS ANY LENGTH INPUT WITHOUT VALIDATION OR ERROR MESSAGE
SEVERITY | MAJOR
PRIORITY | MEDIUM
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/1TeaLdQhy9ZRlW592rxnA5CSQe9VboXTl/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION

## 15
DEFECT_ID | DEFECT_015
MODULE | SEARCH
SUMMARY | SEARCH FUNCTION RETURNS INCOMPLETE RESULTS FOR VALID KEYWORD
DESCRIPTION | WHEN THE USER SEARCHES FOR A VALID KEYWORD SUCH AS "CAMERA", THE SYSTEM DISPLAYS ONLY ONE PRODUCT IN THE SEARCH RESULTS. HOWEVER, THERE ARE MULTIPLE PRODUCTS RELATED TO THE SAME KEYWORD AVAILABLE IN THE APPLICATION. THIS INDICATES THAT THE SEARCH FUNCTIONALITY IS NOT FETCHING ALL RELEVANT RESULTS.
STEPS TO REPRODUCE | STEP 1: OPEN THE APPLICATION STEP 2: ENTER "CAMERA" IN SEARCH BAR STEP 3: CLICK ON SEARCH BUTTON STEP 4: OBSERVE THE DISPLAYED RESULTS STEP 5: COMPARE WITH ACTUAL AVAILABLE CAMERA PRODUCTS IN CATEGORIES
EXPECTED RESULT | SYSTEM SHOULD DISPLAY ALL RELEVANT PRODUCTS MATCHING THE SEARCH KEYWORD (E.G., ALL AVAILABLE CAMERA PRODUCTS)
ACTUAL RESULT | ONLY ONE PRODUCT IS DISPLAYED IN SEARCH RESULTS EVEN THOUGH MULTIPLE MATCHING PRODUCTS EXIST
SEVERITY | MAJOR
PRIORITY | HIGH
DEFECT TYPE | FUNCTIONAL ISSUE
ATTACHMENTS | https://drive.google.com/file/d/1jVMtL2m90weJlqMtebswh_PEYGo-aqNs/view?usp=drivesdk
ASSIGNED TO | DEVELOPER
DEVICE DETAILS | HP
OS | WINDOWS
OS VERSION | 11
DEVICE DETAILS | HP
BROWSER | CHROME
BROWSER VERSION
BUILD VERSION